## Sprint 1
Sprint Retrospective
Sprint: | Sprint 1 — Data Collection & Engineering
Epic: | Epic 1: Data Collection & Engineering
Dates: | 1 Feb – 8 Feb 2026 (7 days)
Team: | Yash Chauhan (YC), Shreya Srivastava (SS)
Scrum Master: | Prof. Suresh Kumar Chelliah
Sprint Goal: | Collect verified government data from 7 sources via web scraping, merge using inner join, and compute composite indices (DAS, CEBS, DCI).
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
All 7 government data sources (TRAI, RBI, NITI Aayog, NPCI, CPCB, Census) successfully identified and scraped within 5 days. | TRAI PDF did not have a downloadable CSV — required manual extraction from tables, adding extra time. | For future studies, contact CPCB directly to obtain missing state data before starting analysis. | Include weight sensitivity analysis in Sprint 3 to prove results are not weight-dependent.
Web scraping scripts worked reliably across all portals — data extraction was smooth. | CPCB e-waste data only covered 24 entities — 5 key states (Goa, Telangana, UP, Uttarakhand, WB) missing. | Automate TRAI PDF parsing using tabula-py or camelot to eliminate manual extraction. | Document the inner-join decision and its trade-offs in the paper limitations section.
Inner-join strategy was a strong team decision — eliminated data quality concerns entirely. | Inner join reduced sample from 29 states to only 16 — smaller sample raises statistical power concerns. | Document weight rationale more formally in the methodology — include sensitivity analysis upfront. | Save all raw scraped data with timestamps for reproducibility and audit trail.
Composite indices (DAS, CEBS, DCI) designed with clear rationale and validated formulas. | Weight allocation for DAS/CEBS required multiple guide consultations before finalizing. | Consider building a reusable web scraping pipeline that can be scheduled for periodic data updates. | Set up data validation checks in the pipeline to catch any scraping errors automatically.
Cross-validation of TRAI scraped data against published PDF showed 100% match — zero errors.
Complete dataset (16 states x 15 variables) generated with zero missing values.
Sprint Outcome: Stories Planned: 10 ¦ Stories Completed: 10 ¦ Velocity: 10 story points ¦ Completion: 100%
Key Outcome: Unified dataset created (16 states x 15 variables) with zero missing values. All data traceable to official government publications.

## Sprint 2
Sprint Retrospective
Sprint: | Sprint 2 — Exploratory Data Analysis
Epic: | Epic 2: Exploratory Data Analysis (EDA)
Dates: | 10 Feb – 13 Feb 2026 (4 days)
Team: | Yash Chauhan (YC), Shreya Srivastava (SS)
Scrum Master: | Prof. Suresh Kumar Chelliah
Sprint Goal: | Generate 8 publication-ready figures to understand data distributions, correlations, rankings, and trends before hypothesis testing.
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
All 8 EDA figures generated in just 4 working days — efficient sprint. | NPCI monthly Excel files had a different format than per-capita data — caused extra hours of reformatting. | Standardize all data input formats at the scraping stage to avoid downstream reformatting. | Update 02_eda_visualizations.py with matplotlib style configuration at the top of the script.
Correlation heatmap immediately revealed strong DAS-CEBS relationship (R squared = 0.610) — key finding validated visually. | Initial color scheme was not colorblind-friendly — had to redo 3 figures. | Use a consistent color palette (e.g., viridis or cividis) for all figures to ensure accessibility. | Use seaborn built-in colorblind palette for all remaining figures.
Box plots showed clear step-wise CE improvement by digital access group — intuitive and presentation-ready. | DCI ranking chart initially had overlapping state labels — needed horizontal bar redesign. | Create a figure style template that can be reused across all scripts. | Create a shared config.py with figure dimensions, fonts, and DPI settings.
UPI trend analysis (20 months) added temporal dimension that strengthens the narrative. |  | Add interactive versions of figures using Plotly for the presentation. | Review all figures for consistency before moving to statistical analysis.
All figures are publication-quality with proper annotations, labels, and color schemes.
Sprint Outcome: Stories Planned: 8 ¦ Stories Completed: 8 ¦ Velocity: 8 story points ¦ Completion: 100%
Key Outcome: 8 publication-ready EDA figures generated. Correlation heatmap confirmed strong DAS-CEBS link (R squared = 0.610).

## Sprint 3
Sprint Retrospective
Sprint: | Sprint 3 — Statistical Hypothesis Testing
Epic: | Epic 3: Statistical Hypothesis Testing
Dates: | 15 Feb – 27 Feb 2026 (13 days (2 weeks))
Team: | Yash Chauhan (YC), Shreya Srivastava (SS)
Scrum Master: | Prof. Suresh Kumar Chelliah
Sprint Goal: | Test H1 (DAS to CEBS), H2 (UPI mediation), H3 (tele-density threshold) using OLS, robustness checks, bootstrap, and extended sample analysis.
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
H1 strongly supported (r = 0.781, p < 0.001) — core finding is robust and clear. | H2 (UPI mediation) was NOT supported — Sobel p = 0.810. This was unexpected and required re-interpretation. | Frame the H2 rejection as a positive research contribution — broad infrastructure effects, not just payments. | Write a dedicated Reviewer Defense section in the paper documenting all robustness checks.
Non-parametric tests (Spearman rho = 0.912, Kendall tau = 0.783) confirmed OLS results without normality assumptions. | H3 threshold analysis has a caveat — only 2-3 states above the threshold of 118.77%. | Explore alternative mediation variables beyond UPI for future research. | Explicitly note the Haryana outlier in limitations and show results hold without it.
Bootstrap CI (10,000 iterations) conclusively excludes zero — strong defense for small n. | Cooks Distance flagged Haryana (D = 4.16) as highly influential — needed additional robustness checks. | Consider jackknife resampling to complement bootstrap for reviewer defense. | Add a clear caveat about above-threshold sample size in the H3 discussion.
Weight sensitivity analysis (6/7 schemes significant) proves results are not an artifact of weight choice. | Sprint took 2 weeks instead of planned 1 week due to the volume of robustness checks needed. | Plan a follow-up study with longitudinal data to strengthen threshold analysis. | Include the VIF explanation (expected due to shared NSDP component) in the methodology.
HC3 robust standard errors (p = 0.000011) and permutation test (p = 0.0001) provide reviewer-proof defense. | VIF for DAS in multiple regression was 10.57 — multicollinearity is a concern that needed explanation.
Extended sample analysis (n = 21, r = 0.963) shows relationship gets stronger with more data.
All diagnostics pass — no heteroskedasticity (BP p = 0.215), no autocorrelation (DW = 2.025).
Sprint Outcome: Stories Planned: 12 ¦ Stories Completed: 12 ¦ Velocity: 12 story points ¦ Completion: 100%
Key Outcome: H1 SUPPORTED (r = 0.781, p < 0.001), H2 NOT SUPPORTED (Sobel p = 0.810), H3 SUPPORTED (threshold at 118.77%). 12 robustness checks all passed.

## Sprint 4
Sprint Retrospective
Sprint: | Sprint 4 — Machine Learning Validation
Epic: | Epic 4: Machine Learning Validation
Dates: | 1 Mar – 7 Mar 2026 (7 days)
Team: | Yash Chauhan (YC), Shreya Srivastava (SS)
Scrum Master: | Prof. Suresh Kumar Chelliah
Sprint Goal: | Validate statistical findings using 7 ML models (LOO-CV), XGBoost (nested CV), and stability analysis (400 splits).
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
LOO-CV with full features (Lasso R squared = 0.568) is consistent with OLS R squared = 0.610 — confirms no overfitting. | SVR completely failed (R squared = -0.023) — wasted time on hyperparameter tuning before concluding it is unsuitable. | For future work, use GPU-accelerated XGBoost to speed up nested CV computations. | Document the SVR failure in results — it provides useful information about data characteristics.
Digital-only features predict 36.4% of CE variance — validates that digital access has independent predictive power. | XGBoost installation on macOS required libomp dependency — caused setup delay. | Investigate why Haryana is consistently an outlier — may have unique policy factors. | Add libomp installation step to README for reproducibility on macOS.
XGBoost nested LOO-CV achieved R squared = 0.511 with zero data leakage — gold-standard estimate. | Nested CV is computationally expensive with LOO outer loop — took considerable time to run all 6 models. | Consider adding LightGBM and CatBoost to the model comparison for a more comprehensive benchmark. | Include computational cost comparison in the ML results section.
Repeated K-Fold CV (400 splits) identified RF as most stable model — adds reliability evidence. | Haryana remains the largest prediction outlier (CE = 87.3 vs predicted 56) — consistent with Cooks D finding. | Implement a model stacking approach to potentially improve prediction accuracy. | Ensure all model hyperparameters are logged for reproducibility.
Per-state predictions show Maharashtra most accurate (error = -0.08) — useful for policy discussion.
Sprint Outcome: Stories Planned: 10 ¦ Stories Completed: 10 ¦ Velocity: 10 story points ¦ Completion: 100%
Key Outcome: XGBoost nested LOO-CV R squared = 0.511 (zero data leakage). Lasso LOO-CV R squared = 0.568 matches OLS R squared = 0.610 — no overfitting.

## Sprint 5
Sprint Retrospective
Sprint: | Sprint 5 — Explainability, Clustering & Paper
Epic: | Epic 5: Explainability & Clustering
Dates: | 10 Mar – 15 Mar 2026 (6 days)
Team: | Yash Chauhan (YC), Shreya Srivastava (SS)
Scrum Master: | Prof. Suresh Kumar Chelliah
Sprint Goal: | Apply SHAP for feature attribution, K-Means for state typologies, PCA for visualization, and compile all findings into IEEE conference paper.
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
SHAP analysis conclusively shows Tele-density (rank 1) and NSDP (rank 2) drive CE predictions — aligns with statistical findings. | Initial SHAP computation was slow on CPU — had to switch to TreeExplainer for speed. | Create a Streamlit dashboard for interactive SHAP explanations and state comparisons. | Submit paper.tex to the target IEEE conference by the deadline.
SHAP waterfall plots for Haryana and Bihar provide clear, actionable state-level explanations. | LaTeX subfig package conflicted with caption package — required debugging and package removal. | Use hierarchical clustering as a complement to K-Means for more nuanced state groupings. | Archive all code, data, figures, and results in a single reproducible zip file.
K-Means clustering (k = 2) cleanly separates Digital Leaders (DCI = 46.7) from Emerging States (DCI = 18.3). | Paper length was initially 8 pages — had to compress to 6 pages per IEEE format. | Prepare a supplementary materials document with all robustness checks for the paper. | Prepare a 10-minute presentation with key SHAP waterfall and clustering visuals.
PCA explains 84% of variance in just 2 components — clean dimensionality reduction. | Several figures needed resizing to fit IEEE two-column format without losing readability. | Consider submitting to multiple conferences (IEEE and Springer CCIS) for wider impact. | Share the project repository with the research guide for final review.
IEEE paper compiled successfully — all 22 figures embedded, all numbers verified against result files.
Full project completed on schedule — all 40 user stories delivered across 5 epics.
Sprint Outcome: Stories Planned: 8 ¦ Stories Completed: 8 ¦ Velocity: 8 story points ¦ Completion: 100%
Key Outcome: SHAP confirms Tele-density as top driver. Two state clusters identified (Digital Leaders vs Emerging). IEEE paper compiled and verified.